## Work Breakdown Structure
% complete | WBS | TASK | OWNER
100 | 1 | Select housing dataset | team
100 | 1.1 | Determine where to house it | team
80 | 1.2 | Pare down the size of the dataset | Jennifer
| 2 | User Interface
| 2.1 | Design the user interface
90 | 2.1.1 | Identify input and output fields | team
50 | 2.1.2 | Identify visualizations | team
| 2.2 | Determine tools to use (javascript, flask, Folium) | team
| 2.3 | Develop integration with model
| 2.3.2 | send input data to model | Nicolette
| 2.3.3 | receive output data from model
| 2.4 | Build landing/user input form | Deb
| 2.5 | Create/display visualizations
| 2.5.1 | Map of house prices | Kelly
| 2.5.2 | Graph of prices over time
| 2.5.3 | Model results: Predicted Sale Price +/- margin of error
| 2.6 | Create website | Nicolette
| 3 | Price Prediction Model
| 3.1 | Design price prediction model
| 3.1.2 | Feature engineering
| 3.1.2.1 | identify location-based data and sources (crime rates, school ratings, walkability scores, distance to amenities)
| 3.1.2.2 | identify economic indicators and sources (interest rates, employment rates, housing demand)
| 3.1.2.3 | identify any features that need to be engineered (price per sf, seasonal trends, etc)
| 3.2 | Select model | Janice
| 3.2.1 | Start with linear regression for baseline predictions
| 3.2.1 | Improve accuracy using Random Forest, Gradient Boosting ro Neural Networks
| 3.3 | Data preprocessing and cleaning | Jennifer
| 3.3.1 | remove outliers that skew the model
| 3.3.2 | normalize or standardize numerical values
| 3.3.3 | fill missing values using statistical imputation
| 3.3.4 | convert categorical variables into numerical representations
| 3.4 | Training and validation
| 3.4.1 | Use cross-validation to prevent overfitting
| 3.4.2 | Ensure a balanced dataset representing different price ranges and home types
| 3.4.3 | Perform hyperparameter tuning for optimization
| 3.5 | Evaluate and refine the model
| 3.5.1 | Evaluation metrics
| 3.5.1.1 | Use R2 score, mean aboslute error (MSE), root mean squared error(RMSE) to measure accuracy
| 3.5.1.2 | Compare results across different machine learning models
| 3.5.2 | Test predictions against real market listings for validation
| 3.5.3 | continuously update the model with new data trends

## UI Requirements
User Input | Data | Description | Format | Comment
| Market Date | Anticipated date for house to be put on the market | MM/DD/YY | Is this even relevant since the data is old?
| Finished SF | Size of house in finished square feet | Integer
| SF Lot | Size of lot in square feet | Integer
| Bedrooms | Number of bedrooms | Integer
| Bath Full | Number of full baths | Integer
| Bath 3/4 | Number of 3/4 baths | Integer
| Bath half | Number of half baths | Integer
| Stories | Number of stories | Float
City
Subdivision
Data Questions
What is SeaTac vs SEA-TAC?
Should we express lot size in acres? (divide SF by 43560)

## Sheet1
ideas
how long will it take to sell (days)?
price per sf
how much does a view affect the price per sf
compare home size and lot size - how does this affect the price?
join in other data - weather patterns
how valuable is having a finished basement

## Model Features
sale_id
sale_date | parse out year
sale_price | TARGET
sale_nbr
latitude
longitude
city
zoning | determine cutoff and bucket as "other"
subdivision | too many to use
land_val | create buckets
imp_val | create buckets
year_built | create buckets
year_reno | not always
sqft_lot
sqft
sqft_1
sqft_fbsmt
grade
fbsmt_grade
condition
stories
beds
bath_full
bath_3qtr
bath_half
garb_sqft
gara_sqft